## Bankstown Girls High School

## School Plan

## 2009 - 2011

| School Context |  | Bankstown Girls High School is a comprehensive high school comprising of approximately 689 girls from diverse cultural, religious and socio-economic backgrounds. 98% of the girls are from language backgrounds other than English, predominantly Middle Eastern, South-East Asian, Pacific Islander, Chinese, and West African. The cultural demographics of the Bankstown area shifts with changes in federal and state policies related to immigration, housing, and employment. Many of the families in the area are now second generation Australians. None-the-less many parents and guardians still require interpreters and translators to fully access school information and during parent interview. There is a growing number of refugee, international full fee paying and Intensive English Centre students enrolling throughout the year. There are approximately 69 staff including school administration officers, one school administration manager, a general assistant, full-time cleaning, full and part-time permanent and temporary teachers, 1 part-time counsellor, 8 head teachers, 2 deputy principals and the principal. Of the permanent and temporary staff there are a number of early career and New Scheme teachers. A substantial number of staff have teaching experience in excess of 10 years. A high percentage of staff come from multicultural backgrounds and are bilingual. The school community have high expectations for the girls, but often lack the skill, knowledge, and understandings to effectively support their daughter’s in selecting appropriate educational and employment pathways. The school’s student welfare, curriculum, teaching and learning and community participation programs recognise and proactively address this gap. The curriculum allows for girls aspiring to post-school studies and work through an extensive curriculum incorporating extension courses in English, mathematics, and history; as well as, VET and Life Skills courses. Girls are supported from year 7 to 12 with comprehensive developmental programs from a four week year 7 Orientation program, “Staying on Track” in Year 9, “Decision Time” in Year 10, and individual course counselling and mentoring in Years 11 and 12. These programs are well supported by our Learning Support and Welfare Teams, Transition and Careers Advisers, and Middle School and Enrichment coordinators. The school’s primary focus is on quality teaching and learning. Over a 3 year period, 2002 – 2004, the teachers have engaged in a school based Pedagogy Project focusing on Intellectual Quality (higher order thinking skills) supported by PSP (Priority Schools Program). In 2005 -2008 our Pedagogy Project focused on significance and knowledge transfer, ensuring learning programs is relevant to students within and outside of school. The focus for 2010 -2011 is on consolidation of our pedagogy practices and the development of a Collaborative Learning Interactive Community (CLIC), an e-learning community involving the whole school and our partner school Bankstown Public. The priority for 2009 -2011 is “Plus 3 Points” focussing on Quality Teaching, student feedback and strategic questioning. The school has an integrated IM (mild intellectual disability) program focussing on students in Years 7 to 10, which is operates on an inclusive model to provide students with both individual targeted support and opportunities to integrate with mainstream peers. The school is located geographically within the Bankstown CBD allowing for convenient access to local businesses, community organisations, and transport. The grounds of the school are compact but brightly finished two covered areas to shelter students in their breaks. Unfortunately, the school lacks playing fields and must access the council ground adjacent. The school has strong links with agencies and organisations within the community in particular Bankstown Sports Club, Legacy, Rotary, Bankstown City Council, Lebanese Welfare Association, Pacific Communities network, and The Corner Health team. # Awarded Regional Awards for Excellence in ESL Education (2007), Sports Education (2009), ICT Teaching (2009), and named “School of the Year” by the Australian Lebanese Association for our integrated whole school literacy, numeracy and thinking skills programs in 2005. In 2009 the highest Australian Tertiary Admission Rank (ATAR) was 96.25. |  |  |
| --- | --- | --- | --- | --- |
| # We are committed to the provision of effective learning in a caring, supportive, co-operative environment. We value the individuality and talents of each student. We seek to develop self-esteem and positive attitudes towards being female, and to ensure that each student is empowered to reach her potential. We encourage tolerance and harmony through an understanding of other cultures. This will be enhanced by the involvement of the school community as a whole and the preparation of our students for responsible citizenship. |  |  |  |  |
| Student Exit Outcomes | Academic Outcomes A young adult who is: - Literate: will be able to write, read, listen, and speak appropriately in a range of contexts using critical analysis in order to meaningfully function in society. - Numerate: will be able to think mathematically and apply mathematical tools confidently for different purposes and contexts. - A critical thinker: will be able to evaluate alternatives, make judgements based on sound reasoning, or justify a position, stance, or point of view. - Technological: will be able to combine their artistic, conceptual, and practical skills to solve problems. - A problem solver: will be able to IDENTIFY relevant facts, PLAN appropriate strategies and operations, SOLVE the problem and REVIEW the process and solution. - An inquisitive learner: will actively seek knowledge by being an interested and curious learner. - An independent learner: will take responsibility for their learning and show initiative. - Demonstrating achievement of KLA outcomes: will have an understanding of subject content, skills, and values. |  | Social Outcomes A young adult who is: - An effective communicator: will appropriately convey information clearly and successfully; - Cooperative: will willingly work in harmony with others towards a common goal; - Civic Minded: will have a sense of belonging to the wider Australian community and participate as a constructive member; - Respectful: will display positive regard based on awareness and/or knowledge of someone or something; - Generous of spirit: will be open hearted; - Courteous: will be polite, well mannered, attentive and considerate of others; - Responsible: will accept moral accountability for his/her actions and will be trustworthy and reliable; - Motivated: will be determined, inspired and energetic, with drive and desire; - Honest: will be fair to others, truthful and trustworthy. |  |

Teacher Quality

Develop and build the capacity of teachers to be leaders of learning in a technology rich quality learning environment.

2009 - 2011

PRIORITIES

Informed by data/evidence, needs analysis & state plan targets

Literacy

All students consistently achieve higher levels of literacy in line with the state plan targets.

2010 Targets

Engagement & retention

All students are engaged in and challenged by a 21st. century learning environment and achieve academic and/or vocational success.

Numeracy

All students consistently achieve higher levels of numeracy in line with the state plan targets.

MANAGEMENT AREAS

Programs incorporating strategies to achieve school targets and focus resources on school priorities

Teaching & Learning

Student Support & Well-Being

Professional Learning

School & Community Partnerships

Physical Resources & Administration

Target 1

To match the school average for literacy achievement in both Year 7 & 9 NAPLAN to the State average.

Strategies:

Focus on explicit and sustained reading & the development of spelling, grammar and punctuation in all KLAs years 7-10

Strengthen and empower the cross KLA expert literacy team to support teachers in the development and delivery of strategies using both traditional and interactive technologies through the Learning Portal (CLIC)

Measured by:

The school’s value-added data consistent with the state growth in literacy for Years 7-9;

Increase the number of students achieving in the higher bands in reading and grammar for Years 7 and 9 NAPLAN;

25% of students achieve a Band 5 or 6 in School Certificate English Literacy test.

Target 2

To match the school average for numeracy achievement in both Year 7 & 9 NAPLAN to the State average.

Strategies:

Numeracy strategies e.g. Counting On and START cards, actively implemented in all classrooms

Focus on explicit teaching of data and measurement across all KLAs years 7-10

Cross KLA expert numeracy team established to support teachers in the development and delivery of strategies using both traditional and interactive technologies through the Learning Portal (CLIC)

Measured by:

The school’s value-added data consistent with the state growth in numeracy for Years 7-9;

Increase the number of students achieving in the higher bands in overall numeracy for Years 7 and 9 NAPLAN;

15% of students achieve a Band 5 or 6 in School Certificate Mathematics test.

Target 3

Focus on high expectations in every classroom.

Strategies:

All teachers explicitly and actively promote “Plus 3 Points” strategies in every class for all students;

Embed powerful questions and regular explicit  feedback into faculty practices

Teaching for transfer and significance in Stage 5 programs through the delivery of the Year 9 Project and programs

Individual Learning Plans for all ATSI students

Explicit teaching of core technology skills in KLAs

Measured by:

Improved individual growth beyond state growth in NAPLAN;

Improved SC to HSC value added across all achievement levels.

Increase number of students progressing into higher bands for NAPLAN, ESSA, SC, CSA & HSC

Maintain attendance at or above State and Regional averages.

Target 4

At least 95% of Year 10 students progress to the HSC or recognised vocational training.

Strategies:

Comprehensive individualised transition process for all students in Years 7–12 supported by a Transition Coordinator

Explicit teaching of student self-direction and management skills included in KLA programs supported by the Enrichment Officer.

Proactive and inclusive student leadership programs

Balance of extracurricular activities

Exit survey to track student destinations Years 10 -12

Parents well informed and involved in transition programs from Yr 6-12.

Measured by:

Number of students successfully transitioning to further study or full-time work;

Retention data at HSC at 80%;

Attendance data for Year 11 & 12 at or above State and Regional averages.

Parent meeting attendance

Target 5

All staff engages in professional learning programs to enhance their capacity to improve student outcomes and support and/or lead school improvement.

Strategies:

Further develop SharePoint CLIC site to support the school’s priority areas of literacy, numeracy, thinking, student self-direction, knowledge transfer, high expectations and interactive technologies.

Continue to build on the Aspiring Leaders /Shadows program

Measured by:

Increase number of students progressing into higher bands for NAPLAN, ESSA, SC & HSC

CLIC site operational across the school

100% of staff participating in PL programs

Increase in teacher expertise in target areas of literacy, numeracy ICT, effective feedback, strategic questioning & career planning.

|  | SCHOOL IMPROVEMENT | TEACHING AND LEARNING | PROFESSIONAL LEARNING | STUDENT SUPPORT | SCHOOL & COMMUNITY PARTNERSHIPS | PHYSICAL RESOURCES & ADMINISTRATION |
| --- | --- | --- | --- | --- | --- | --- |

| Management Teams | Betty Harper (Principal) Mark Leary (Deputy) Charles Borg (Deputy) Kylie Rytmeister (HT TAS) Elizabeth Kyritsis G O’Keefe (HT Admin) |  | C Porreca (HT T&L) J Tsafis (HT HSIE) E Nadile (CLIC coord) N Barnes D Alembakis (Enrich. Officer) K Rytmeister (HT TAS) E Hidalgo E Kyritsis (VET coord) G Kalatzis D Voros (Middle School coord) H Hawkins (Librarian/Debating) A Mustapha (numeracy coord) D Dymond (Literacy coord) J Gibbons (HT Sci/ Ab. Ed) M Hundy (Careers Adviser) D Wu G. O’Keefe C. Solis M. Tsoutras VSaisanas (HT Maths) | Lisa Carmody (HT English) Mark Leary (Deputy) S Prasad N Hassan NST/ECT T Pistolis (PC) M Carthew C Solis (PC) H Bevilacqua (NST) S Karim N Theodoridis (T/PC) K Mohan (T/NST) T Zouridis (T/NST) R Fitzsimons (T/NST) S Majanggil (T/NST) T Zouroudis (T/NST) N Kheedoori (T/NST) J Khatib (T/NST) Verity Cash (T/NST) B Arambatzis (T/NST) | J Hardy (HT Welfare) C Stamm (YA12) H Jackson (YA 11) R Stevens (mentor) T Pistolis (YA 8) L Kelly (YA 7 – Shadow HT) H Yang (YA 9) M Salerno (YA 10) C Dalton (SRC) (PC) O Yilmazlar (YA 6) Learning Support Team C Porreca (HT T&L) D Dymond (STLA) S Lane (IM) S Templeman (counsellor) B Harper C Borg M Leary S Cole/N Khedoori (Transition Adviser) M Hundy (Careers Adviser) J Hardy (HT Welfare) | D Clarke (HT PDHPE) S. Fifita (PI CLO) M Hundy I Stangoulis O Yilmazlar G Dennaoui (Arabic CLO) Z Shah E Vassiliou M Tsoutras(PC) C Borg (Deputy) | G O’Keefe (HT Admin) B Harper C Borg M Leary L Holland (SAM) J Gibbons (OHS) J Scott (GA) M Papas (OHS) J Tsafis (Finance c’tee) M Salerno (Finance c’tee) L Kelly (Finance c’tee) D Clarke (Finance c’ttee) E Kyritsis (Finance c’ttee) C Porreca (Finance c’ttee) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Purpose |  | To ensure the continued alignment of our school’s vision, purpose, student exit outcomes and standards in all programs and practices. To apply this shared framework to all actions, building consistency across the curriculum and ensuring “learning for a changing future”. | To support our integrated approach to educating the “whole child” by embedding all dimensions of the QT framework across the curriculum, through the backward mapping process to ensure alignment of exit outcomes, curriculum pedagogy, and assessment. | To support the development of a professional learning community through our commitment to QT, collaboration, the development of leadership capacity and planned succession. | To build on our shared values of inclusivity, celebration of diversity and high expectations through the development of effective student welfare programs which enhance congruence of expectations and achievement in a caring and tolerant community. | Building positive relationships with our parent body and the broader community, including other educational institutions, industry and business. Facilitating opportunities and build on their knowledge and understanding of the NSW education system. | To continue to develop effective resource management and infra- structure that maximises support of our holistic and integrated approach to quality teaching and curriculum, and the school targets, whilst maintaining the capacity to be responsive to emerging needs. |

school culture

SCHOOL IMPROVEMENT

Aligning

DET & School Policy, Planning & Practice

with

long term Priorities & annual Targets

through

a cycle of evaluation

PSFP

Curriculum

Faculty

Self evaluation

PHYSICAL RESOUCES & ADMINISTRATION

Staffing

Finance committee

Communication: assemblies, daily notices, calendar, newsletters, home/school notices

Attendance monitoring systems

Timetable

OH&S

Accidents & Workers Compensation

Assets management

Community use of facilities

Site maintenance

Exam organisation

Rosters

Returns

Canteen

Variations to routine

STUDENT SUPPORT

Student welfare team

Middle school & transition programs

Year 7 Orientation program

Student management, discipline & attendance

Appeals committee

SRC & Leadership programs

ESL, Integration, IEC & International students

HSLO referrals

Peer Support

Senior Mentoring program

Year Advisers

Junior and Senior Reviews

Student awards

Uniform

Anti Bullying

Drug Education

PROFESSIONAL LEARNING

Beginning Teachers – Inductions

New staff orientations

Executives, SASS, KLA development & support

Staff meetings

School Development Days

TARS

Mandatory compliance training

Staff welfare & morale

TPL administration

Trainee teachers

TEACHING & LEARNING

Middle School and Transition programs:

Year 7 Orientation Program

Yr 9 “Staying on Track”

Careers/Pathways and transition to work

Primary school links programs

Scientific Literacy

SharePoint project with BPS

Year 9 Cross curricular Project

Assessment & reporting

Curriculum

Sport, Cross Roads, Drug Education

Equity programs: GAT, Multicultural, Girls & Boys Ed, Aboriginal, CSA10

Literacy, Numeracy, Technology, Study Skills

Thinking skills development

Learning Support programs: STLA & IM, Disability, ESL, Learning Centre

Challenge Corner

VET/TVET

Debating/public speaking

COMMUNITY & SCHOOL PARTNERSHIPS

Parent meetings & network s

Information evenings’

Promotion & publicity

School newsletters

Parent workshops

Industry & business links

CLOs

Special school events

| Proposed Income | $ | Proposed Expenditure | $ |
| --- | --- | --- | --- |
| Funds Carried Forward from 2009 | $462,560.77 | Educational Programs |  |
| 2009 AFS balances - Tied | $101,018.41 | Faculties | $ 50,372.00 |
| 2009 AFS balances - Trust | $43,267.38 | Anticipated subject fees ($65%) | $ 21,242.00 |
| 2009 AFS Unpaid orders,invoices,salaries | $40,037.23 | Professional Learning | $ 5,000.00 |
| 2009 AFS Provision Asset replacement | $45,000.00 | Trust expenditure | $ 56,000.00 |
| 2009 AFS Provision for additional assets | $64,000.00 | Tied expenditure | $ 112,300.00 |
| Total committed | $293,323.02 | TPL - $28000 |  |
| balance discretional funds | $169,237.75 | Syllabus implementation | $ 7,500.00 |
|  |  | Quality Teaching | $ 7,500.00 |
|  |  | Career Devt | $ 5,000.00 |
|  |  | Technology | $ 2,500.00 |
| Anticipated Income 2010 |  | Beginning teachers | $ 2,500.00 |
| Global - Annual entitlement | $ 305,203.00 | Literacy/Numeracy | $ 1,000.00 |
| Tied grants: PSP/TPL/ | $ 223,800.00 | Welfare & Equity | $ 2,000.00 |
| Trust | $ 56,000.00 | PSFP - $83500 |  |
|  |  | CLIC $11,044 Enrichment $22304 Literacy/Numeracy $11,152 | $ 44,500.00 |
|  |  | Community $39,000 | $ 39,000.00 |
|  |  | Technology | $ 50,000.00 |
|  |  | International Student | $ 25,000.00 |
| School Contribution | $ 36,340.00 | Sport | $ 5,870.00 |
| Subject Fees | $ 34,450.00 | Excursions incl. Sport activities | $ 88,500.00 |
| Canteen Lease/Hire of facilities | $ 23,200.00 | Library | $ 10,000.00 |
| Uniform shop/Sales to Students | $ 2,000.00 | Middle School | $ 1,540.00 |
| Overseas students | $ 28,800.00 | OHS | $ 2,120.00 |
| Excursions | $ 60,000.00 | Performing arts/Presentation Day | $ 7,120.00 |
| Sport | $ 28,500.00 | Student Support & welfare | $ 2,730.00 |
| Bank interest | $ 20,000.00 | Careers | $ 2,850.00 |
| GST | $ 48,500.00 | SRC | $ 1,500.00 |
| Casual Salaries cross curr | $ 10,000.00 | Support | $ 3,100.00 |
| Miscellaneous | $ 6,800.00 | other special programs | $ 3,305.00 |
|  | $1,052,830.75 | Purchases for resale | $ 2,000.00 |
|  |  | Utilities | $ 80,850.00 |
|  |  | Extra Curricular salaries | $ 25,000.00 |
|  |  | Casual Salaries | $ 80,000.00 |
|  |  | Administration | $ 133,995.00 |
|  |  | Maintenance - Bldg, Grounds, Equip | $ 47,000.00 |
|  |  | TOTAL EXPENDITURE | $ 928,894.00 |
|  |  | BALANCE | $123,936.75 |

| MANAGEMENT AREA |  | School Improvement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| School Priority | Expected Outcomes and Targets | ###### Implementation Strategies | 2010-11 | # Responsibility | Indicators of Success | Allocation $ | Funding source |
| Literacy Numeracy Engagement & retention Teacher quality | - All staff engages in professional learning programs to enhance their capacity to improve student outcomes and support and/or lead school improvement. - At least 90% of Year 10 students progress to the HSC or recognised vocational training. - To match the school average for literacy achievement in both Year 7 & 9 NAPLAN to the State average - To match the school average for numeracy achievement in both Year 7 & 9 NAPLAN to the State average. | Monitor and evaluate school plan - maintain regular meetings in terms 3 and 4 - Apply the evaluation cycle to school programs - Maths - Enrichment Program - Whole school curriculum - Analyse data and evidence collected from teams and staff - Review targets for 2011 - Inform management teams of findings and recommendations | T 3,4 2010 Term 3 2010 Term 4 2010 | B Harper Evaluation teams B Harper SI Team | - Curriculum and Management evaluations completed and published - Data collected, analysed and recommendation published - Targets prepared for 2010 | $3000 (exam supervisors) | Global |
| Literacy Numeracy Engagement & retention Teacher quality | - School community is involved in the collection and analysis of school achievement and performance data - To meet all school targets | Public reporting of targets, priorities and achievement - evaluation of data - completion and publication of reports | Ongoing T4 2010 T1 2010 | B Harper School Improvement team | - ASR completed and distributed - Data analysis informs planning for 2010 -11 - Evaluation of data informs progress of 2010 initiatives and programs - School community well informed about the direction and achievements of the school. | $200 (ASR) | Global |

| MANAGEMENT AREA |  | Teaching and Learning |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| School Priority | Expected Outcomes and Targets | ###### Implementation Strategies | 2010-11 | # Responsibility | Indicators of Success | Allocation $ | Funding source |
| Engagement & retention | - All staff engages in professional learning program to enhance their capacity to improve student outcomes and support and/or lead student improvement | CLIC – Collaborative Learning Interactive Community (Microsoft SharePoint) - Align DER laptops with SharePoint – emphasis on teacher/student collaborative partnerships for years 9 & 10 |  | Nadile | - Embedding of SharePoint framework in all KLAs as information, collaboration and interactive tool - Number of teachers and classes actively using CLIC (SharePoint) to enhance learning. | $11,044 | PSP |
| Literacy Engagement & retention Teacher Quality | - To match the school average for literacy achievement in both Year 7 and 9 NAPLAN to the state average. - Focus on high expectations in every classroom | Literacy - Use 2008/09 NAPLAN results and the SMART Data package to identify areas of need in literacy at school of specific classes in Year 8 - 11 - Introduce a grammar component into Radical Reading lessons in Years 7 and 8. - Conduct staff workshops to: - Revisit text types to facilitate the explicit teaching - Review assessment tasks and rubrics across KLA’s in Year 7 and 8 to ensure that students’ writing is being assessed for correct spelling, grammar and punctuation. - Assist staff to generate critical literacy questions when working with written and visual texts. - Implement a spelling program in Years 7 and 8 English culminating in a spelling competition. - Investigate the implementation of a comprehensive assessment/testing program in the junior school. - Literacy Team to support teachers across KLA’s in the development and delivery of literacy based strategies using both traditional and interactive technologies. - Continue to provide literacy resources on the shared folder in the school network and in CLIC. - Individual Learning Plans written for underachievers; supervised by the Learning Support Team and facilitated by the SLST in the Learning Centre. | 2010 SDD#1 Term 1 SDD#2 SDD#3 Term 1 Term 2 Faculty meetings Ongoing Term1- 4 | D Dymond All teachers Literacy co-ordinator Expert Literacy Team English Faculty KLA Teachers SLST Learning Support Team | - Improvement in NAPLAN results. - Participation in cross KLA Literacy workshops by members of staff - Strategies promoting the development of critical literacy and sustained writing with an emphasis on the correct use of spelling, grammar and punctuation embedded in Year 7 and 8 teaching programs and assessment tasks. - Bank of teaching strategies available to all staff in shared folder on school network. - Increased engagement in learning by underachievers. | $11,152 | PSP |
| Numeracy Engagement & retention | - To match the school average for numeracy achievement in both yr 7 and yr 9 NAPLAN to the State average - Focus on high expectations in every classroom | Numeracy - Use 2008/09 NAPLAN results and the SMART Data package to identify areas of need in numeracy at school of specific classes in Year 8 - 11 - Focus on explicit teaching of Data & Measurement Yrs 7 to 10 by: - Implementing the use of START cards with particular emphasis on features of different graphs, diagrams and tables across KLAs.. - Collaborating with Maths faculty to ensure that explicit teaching of Measurement/Data is taking place 7-10 - Liaising with cross KLA numeracy team members to ensure that Measurement/ Data is explicitly addressed within the context of the subject area 7-10 - Assisting staff in embedding numeracy teaching strategies in various KLA teaching programs as required. (in particular those strategies which develop an understanding of Measurement and Data) | 2010 SDD#1 Term 1-4 SDD#3 Faculty meetings | A Mustapha All teachers Maths faculty A Mustapha Expert Numeracy Team | - Class tests, NAPLAN results - Level of students engagement - Students’ application across KLA. - Samples of teaching programs - Number of teachers trained | Included above | PSP |
| Literacy Numeracy Engagement & retention Teacher quality | - Focus on high expectations in every classroom | Enrichment - Buzz run during P4 Tuesday - Integrating Murder Under the Microscope into Yr 9 Geography classes - Negotiate, develop and deliver extension programs in core KLAs – involving collaborative program writing and team teaching with teachers of high achievers in Years 7 and 8. Focus on: - Strategic questioning - Explicit and powerful feedback - Lesson and assessment task coding (QT framework) | 2010 Term 1-4 Term 2 Faculty meetings Term 1-3 | Enrichment Officer T Alembakis | - Publishing of school newsletter - Completion of online crime and writing plan of action - Work samples, improved engagement - Number of Year 7/8 core subject teachers trained - NAPLAN results Year 7 2010, Year 9 2011 | $22,304 | PSP |
| Engagement & retention | - Focus on high expectations in every classroom | Middle School - Middle School coordinator - High School for a Day- curriculum taster program over 2 days involving students from partner primary schools - Scientific Literacy project - Year 5/7 Challenge Days | 2010 Term 3 | D Voros | - Evaluation by students - Smoother transition into High School - 2011 enrolment numbers | $7300 $1937 $1490 | Staffing allocation Year 6 Transition initiative Arabic Youth Global |
| Engagement & retention | - At least 90 per cent of yr 10 students progress to the HSC or recognized vocational training | Careers - Expand role of Transition Advisor - Implementation of strategies as identified from P.I. Project – Working to Strength - Orientation of new Careers Advisor - Back to Bankstown market day - Review senior patterns of study to accommodate increase of students staying on. | 2010 ongoing Term 1 Term 1 Term 3 Term 3 | Executive Transition Advisor Careers Advisor Executive/CA | - Retention data - Exit outcomes for leavers | $5117 $1200 | Staff entitlement CDSE Grant global |
| Engagement & retention | - At least 90% of students progressing to the HSC or recognised vocational training - Focus on high expectations in every classroom | Indigenous Education - Formation and implementation of Individual Learning Plans for students of Indigenous backgrounds. Catering for specific needs of students academically and socially. - Formation and Implementation of Individual Learning Plans for students of Indigenous backgrounds. Catering for specific needs of students academically and socially. - Posters ,literature, correspondence via BUZZ, CLIC page made available to students advertising Indigenous events, initiatives, resources - Audit strategies used by KLA’s in programming and syllabus implementation of Indigenous perspectives. - New KLA specific resources presented to KLAs as well as located in the Library - Awareness of needs of Indigenous youth incorporated into the beginning teachers program. | 2010 | Gibbons Learning Support Team | - Student attendance and participation statistics - Student participation rates - Audit and Survey via CLIC - Mapping grid of KLA specific units and syllabus outcomes - Student engagement in workshops (all KLA’s) and ‘National Campaign’ presentations by year 9 - Units of work incorporating Aboriginal perspectives across all year groups/KLA’s - Raised awareness of Indigenous issues. | $500 | Global |
| Engagement & retention | - At least 90 per cent of yr 10 students progress to the HSC or recognized vocational training | VET - Investigate the delivery of Stage 5 VET courses - Investigate with a view to introducing new Stage 6 – CEC VET courses - Prepare for VET Audit | 2010 Term 2-3 Term2 | VET Coordinator E Kyritsis VET Team | - Feedback from RTO, RVEC and VET coordinator - Feedback from staff - Level of interest demonstrated by students - Success of current students in 2009/2010 SC/HSC |  | TAS/HSIE budget VET tied grant |
| Literacy Engagement & retention | - To match the school average for literacy achievement in both yr 7 & 9 NAPLAN to the State average - Focus on high expectations in every classroom | Library - Premier’s Reading Challenge for 7 & 9 - Implementing Radical Reading changes as per Library Review | 2010 | Helen Hawkins Support faculty English faculty | - Performance results on NAPLAN, SC and HSC - Monitoring sheets - Number of participants for Premier’s Reading Challenge | $10,000 | Global |
| Teacher quality | - Focus on high expectations in every classroom - All staff engages in professional learning programs to enhance their capacity to improve student outcomes and/or lead school improvement | PSP: Year 9 Project – Making Learning Meaningful - Teachers as facilitators training – incorporating: - Strategic questioning - Explicit feedback - Applying and using Bloom’s Digital Taxonomy - Delivery of KLA units of work incorporating transfer skills and cross-KLA assessment task. - Skilling of Yr 9 IST students in use of Microsoft SharePoint - Creation of CLIC sites by CLIC coordinator - English Campaign teacher workshop - Year 9 student teams – - Incorporate eportfolios into learning; - Develop cross-KLA assessment task during ‘Team Week’ - Present national campaign incorporating ‘blogfolios’ to showcase: - Self-directed learning; - Higher order thinking; - Knowledge transfer - Use of multi-media. | 2010 – T4 SDD#2 SDD#3 Term 3 Term 3 Term 4 | D Alembakis PSP Coordinator | - Collaboration and blogging between facilitator and team - Creation of relevant and appropriate team presentations - Staff and student surveys (pre & post) | Included in Enrichment funds | PSP |
| Teacher quality | - All staff engages in professional learning program to enhance their capacity to improve student outcomes and support and/or lead student improvement | Technology - Whole school ICT mapping summary - DER training, faculty experts to “train the trainers” in software for laptops - Unified approach to OneNote | 2010 Term 1 Ongoing SDD’s | Rytmeister O’Keefe | - Improved confidence in using technology - Ability to embed technology strategies in teaching programs | See PL | DER TPL TPL |

| MANAGEMENT AREA |  | Student Well Being and Support |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| School Priority | Expected Outcomes and Targets | ###### Implementation Strategies | 2010-11 | # Responsibility | Indicators of Success | Allocation $ | Funding source |
| Engagement & retention | - 90% attendance Years 11-12 - 92% attendance years 7 – 10 - At least 90% of students progress to the HSC or recognised vocational training - Focus on high expectations in every classroom. | ATTENDANCE - Implementation and promotion of changes to Exemption from School Attendance policy - Review truancy procedures – whole school promotion and implementation - Involvement in the Youth Pathways Program - Involvement in the Sister2sister Program - Streamlining attendance monitoring and information transfer between roll call teachers, YAs and HT Welfare - Working with the HSLO to implement strategies for Raising the School Leaving Age - Develop attendance improvement strategies for Senior students | Term 1 Term 1 Term 1 T1 T1/ongoing | HTW, Senior Exec, YAs HT Welfare – Hardy HT Admin – O’Keefe DPs HSLO Transition Coordinator | - Average attendance improves from 2007 data by 2% years 7 – 12 - Data from exit survey and enrolment indicates all students engaged in academic course or vocational pathway - Attendance records are accurate | NIL |  |
| Teacher quality Engagement & Retention | - All staff engages in professional learning programs to enhance their capacity to improve student outcomes and support and/or lead school improvement. - At least 90% of students progress to the HSC or recognised vocational training - Focus on high expectations in every classroom. | WELFARE SYSTEMS AND TEAM - Increase opportunities for professional learning of YAs and Welfare Management Team - Acquisition of Welfare related library resources, periodicals and classroom resources - Simplify communication of Welfare related material around the school using the Welfare Team, School Counsellor, Executive and Staff Meetings - Survey staff on welfare communication systems - Increase the profile of Year Advisors - Formalise roles and responsibilities of all members of the Welfare Team - Strengthen links to Leaning Support Team - Ensure YAs have easy access to Academy Attendance system - YAs to publish student ‘Health Issues’ information to all teachers at beginning of year - YAs with the support of the SRC to organise junior (Yrs 7/8) and senior (yrs 9/10) Merit Assemblies each Semester - YAs to manage their years’ ‘Whole School Approach’ to each student ensuring equitable and consistent application of Merit System. | 2010 T1 T 1 Semester 1 Semester 2 | YAs HT Welfare DPs - Counsellor - YAs - SRC coordinator - SRC delegates | - Results of staff survey on student welfare communication - Increased profile of YAs - Merit Assemblies conducted each semester - Whole School approach organised | $4200 $1000 $500 $400 | TPL budget |
| Engagement & Retention | - To match the school average for numeracy achievement in both Year 7 & 9 NAPLAN to the State average. - To match the school average for literacy achievement in both Year 7 & 9 NAPLAN to the State average - At least 90% of students progress to the HSC or recognised vocational training - All staff engages in professional learning programs to enhance their capacity to improve student outcomes and support and/or lead school improvement. | PROACTIVE WELFARE PROGRAMS - Develop and promote support programs for specific student groups - Pacific Community students - Parent meeting - Mentoring - Community programs - International Students - Teacher mentor - Additional ESL support - Excursions and transition activities - Refugee students - Teacher mentors for cultural groups - Anti-Bullying Program review – - research, develop and write collaborating with teachers, students and community - Incorporate Peer Mediation into anti-bullying program through Bully Busters - Incorporate Cooling Conflicts Program into anti-bullying strategy - Include in Peer Support program - Student Leadership - LIMS Program Yr 8 - STARS Program Yr 9 - Student Breakfasts Peer Support Program - Training year 10 cohort as Peer Support Leaders | 2010 ongoing | - Student Welfare team - HT Welfare - PC CLO - Careers Advisor - S Lane - Templeman (couns) - S Preece - O Yilmazlar - HT Welfare - Years 7 – 10 YAs - YAs, HT Welfare - HT Welfare - DP –CB - SRC - P&C | - PC parents feel included in school operations and life - Increase in PC student attendance - Reduction in PC student truancy - Student satisfaction survey indicates International and refugee students are happy and well adjusted to Bankstown Girls High School - Reduction in the number of repeat bully incidents - Bully Busters Program incorporated with Anti-Bullying Program - Increase in numbers of students attending school camps - Increase in numbers of students successfully completing LIMS and STARS Programs - PBIS Program initiated - Uniform consistently worn and reinforced across the school community | $200 $600 $150 $300 $500 | Global Global CDSE grant International student Fees Global Apex |
| Engagement & Retention | - At least 90% of students progress to the HSC or recognised vocational training | COMMUNITY PARTNERSHIPS - Vaccination Program -3 times annually - Interagency referrals and collaboration ie Youth Health Service, Police Liaison, International Woman’s Day Breakfasts - P&C meetings: - Exchange of information on Welfare Programs. - Collaboration with P&C on Anti-Bullying strategies - Collaboration with P&C on Attendance Strategies - Arabic Student Mentoring Program – coordination and training - Mentoring ‘at risk’ students referred via the Welfare Team - Red Cross blood donations Yrs 11-12 - Reinvigorate cultural exchange program with Sister School - Heathcote High |  | - HT Welfare - Arabic & PC CLOs - Mentors – A Mustapha, R Stevens - SRC coordinator | - Parents are well informed about school and adolescent issues - Reduction in chronic poor attendance - Sister school program operational | $900 $300 $3000 $600 | Global Global Arabic Mentor Program PL |

| MANAGEMENT AREA |  | Professional Learning |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| School Priority | Expected Outcomes and Targets | ###### Implementation Strategies | 2010-11 | # Responsibility | Indicators of Success | Allocation $ | Funding source |
| Literacy Numeracy Engagement and retention | - All staff engages in professional learning programs to enhance their capacity to improve student outcomes and/or lead school improvement | PLANNING WHOLE SCHOOL PROFESSIONAL LEARNING - Collect PL suggestions from staff evaluations, team reports, TARS sheets, school targets, school self-evaluation recommendations. - Promoting PL activities through executive and Professional Learning folder - Literacy, Numeracy, enrichment and CLIC coordinator’s plan and present faculty workshops, and sessions for school development days | 2010 Term 1-4 | L Carmody C Porreca (PSP) HT’s M Leary | - Workshops completed and teachers using strategies in faculty programs - Data collected indicates PL needs met and 100% staff participation | Nil | TPL |
| Literacy Numeracy Engagement and retention | - Focus on high expectations in every classroom - To match the school average for literacy/numeracy achievement in both yr 7 & 9 NAPLAN to the State average | SCHOOL DEVELOPMENT DAYS - School development days to provide staff sessions on analysing SMART data to investigating the literacy and numeracy needs of the students they teach. - Sessions on Powerful Teacher Feedback and Strategic Questioning. - Technology tools to enhance learning |  | (HT T&L) C Porreca Literacy/numeracy coordinators D Dymond A Mustapha Reporting task force | - Workshop evaluation data - Workshops addressing targets take place on SDDs | $150 x 3 | TPL BT grant |
| Engagement and retention Teacher quality | - Teachers are confident in the use of ICT to enhance classroom practice embedded into T&L programs. - Staff have opportunities to train other staff members in ICT skills | BUILDING TECHNOLOGY SKILLS AND TEACHER LEADERS - Develop technology teaching and learning mentoring program for faculties and teachers to access. - Build the technology team’s skills in leadership as trainers and mentors - Map a mentoring buddy program for teachers and faculties |  | Technology committee and Tech Team | - Workshops happened - Facilities booking mentors to provide PL program | $2 500 | TPL |
| Numeracy | - Build the capacity of the numeracy team to assist facilities to embed numeracy in their T&L programs. | NUMERACY LEADERSHIP - Apply for PSP consultancy support for the team to develop skills in driving the program. |  |  | - Numeracy team plan and implement faculty PL in the areas language of numeracy, consistent teaching of numeracy skills across KLA’s |  |  |
| Teacher quality | - Leadership Capability is developed at Teacher/ HT/ DP level - Focus on high expectations in every classroom | LEADERSHIP CAPACITY &TEACHER QUALITY - All staff complete a Professional learning plan for 2010 - Continue to deliver the aspiring leaders program, promote and support Aspiring Leaders to attend Regional workshops and promote aspiring leaders as members of school teams /work parties. - Promote the participation of PSP coordinators, technology mentors, senior executive, and executive in regional or state conferences. |  | HT and Teachers P and DP’s HT with teachers SAM with SASS Team leaders/P/ DP | - Number of staff in leadership roles in the school - Number of staff attending leadership PL workshops | $5 000.00 | TPL |
| Literacy Numeracy Engagement and retention Teacher quality | - All NST, New teachers to the school Early career teachers are supported in their development as a teacher and their PL - Increase Early Career Teachers awareness of school & DET procedures | EARLY CAREER TEACHERS - Publish NST/ ECT program to executive and teachers concerned indicating any changes to the program - Identify NST ECT new teachers to the school - Basic Induction program delivered on day 1 - Implement and evaluate a BGHS NST/ ECT conference in early term 1. - Implement and evaluate a support programs for mentors and supervisors of ECT - Promote and support NST, ECT to attend Regional workshops |  | D Clarke and staff coordinating school teams, projects, and programs. ECT Supervisor mentors | - Program is attended by staff and teachers are successful when ready for accreditation. - Mentors established and are active - Participation at Regional workshops | $2 500 $1 500 | TPL |
| Engagement and retention | - Compliance training - All staff engages in professional learning programs to enhance their capacity to improve student outcomes and/or lead school improvement | COMPLIANCE TRAINING - DET requirements/ compliance training - Staff meetings used to address - anaphylaxis and asthma training - OHS, - new Code Of Conduct, - authority to travel and Secondary employment forms - changes to TARS, EARS and PARS and TIPS - Emergency care data base checked and staff to update when required - Resuscitation updating workshop |  | B Harper C Borg M Leary | - Attendance registers | Nil |  |
| Engagement and retention | - Students are engaged at school and in the classroom | STUDENT WELFARE - Develop PL program for Year advisors to drive welfare programs for their cohorts - Continue PL of staff on Mind matters and other welfare programs |  | Ht Welfare Y Advisors Counsellor DP | - PL program implemented and welfare needs for year cohorts mapped and presented e.g. study skills, coping with senior school, being cyber smart. | $2 000.00 | TPL |
| Engagement and retention | - Faculties map the PL for 2010 that will use the TPL grant to improve student learning outcomes | TEACHER QUALITY - Facilities provided with the total of TPL money they will have access - Head teachers to provide the PL plan to DP for 2010 that will be supported by the TPL grant |  | HT ‘s DP | - Movement of student results in external testing | $28 000.00 | TPL |

| MANAGEMENT AREA |  | Physical Resources and Administration |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| School Priority | Expected Outcomes and Targets | ###### Implementation Strategies | 2010-11 | # Responsibility | Indicators of Success | Allocation $ | Funding source |
| Teacher quality Engagement & Retention | - At least 90% of students progress to the HSC or recognised vocational training - All staff engages in professional learning programs to enhance their capacity to improve student outcomes and support and/or lead school improvement. - Focus on high expectations in every classroom. | TECHNOLOGY – access, equity and administration - Easy School Reports program - Continue with SASS and teacher training - Refine report format and functions to include more accurate attendance data - Refine Attendance and Welfare recording program – Academy - Continue Staff training – especially for Welfare team and executives - Refine welfare procedures - incorporate system into school’s welfare and discipline procedures - Ensure access to every staff room and relevant staff - Investigate web-based laptop attendance recording - Connected Classroom in TLS - Improve functionality of room – seating, etc - Staff training - Continue with external ICT support through JAMARK and 1 school ICT coordinator - Develop, publish and implement a 3 year technology plan for the school - DER laptop program - Supervision and professional development of TSO - Establish procedures for distribution and maintenance of Pool laptops for replacement - Establish a pool of discretionary purchased laptops for teacher and Yr 7, 8, 11,12 student use - Develop a PL program for teachers - Purchase of peripheral equipment to maintain laptops eg batteries, chargers, bulk charger, mice, etc. - Develop policies and procedures necessary for smooth implementation and monitoring as needed | 2010 T1 T1-2 T1 T1-2 Sem 1 T1-4 Term 2 Term 1-4 Term 1 Term 1 Term 1-4 Term 2 Term 1-4 | C Borg G O’Keefe C Borg G O’Keefe L Holland J Hardy Jamark G O’Keefe G O’Keefe M Leary C Solis C Solis G O’Keefe K Rytmeister C Borg G O’Keefe S Rahmen S Rahmen G O’Keefe M Leary S Rahmen G O’Keefe | - Parent feedback on semester 1 reports - Evaluation of attendance system at the end of 2008 - decrease in the number of attendance errors - increase number of students accessing technology spaces across the school - Quality of School Life survey | $1,000 $1200 $600 $500 $12,000 $1,000 $24,000 $5,000 $15,000 $30,000 | Global Global TPL Global Global TPL Computer Grant Global TPL/DER TPL Global |
| Teacher quality | - Bankstown Girls High School has a safe and well maintained learning environment - Focus on high expectations in every classroom. | OHS - Upload Emergency Plan to DET site - Maintain OHS documentation in preparation for Audit - Conduct routine workplace inspections each term - Conduct regular communication with staff via Staff and Executive meetings - Conduct 2 evacuation and 1 Lock down drills | Term 1 Term 1-4 Term 1-4 Term 1-4 Term 1,2,4 | C Borg C Borg J Gibbons J Gibbons C Borg | - Evacuation evaluations - Injury and accident data | As required $2,000.00 | TPL Global |
| Engagement & Retention | - Students have a safe and comfortable environment for relaxing and learning | SITE AND ASSET MANAGEMENT - cost seating in the playground areas and establish safe and practical positioning - Update key register | T 2 | G O’Keefe C Borg J Scott (GA) | - Students are happy and sheltered from the elements in the playground - Students and teachers have access to facilities and equipment | $5,000.00 | Global |
|  |  | STAFFING - Ensure all casual & temporary engagement teachers have had security checks, are DET approved, have received all mandatory child protection in servicing, are New Scheme Teachers - Ensure all casual & temporary engagement staff are aware of & follow BGHS staff procedures as established in the BGHS Staff Procedures booklet - Maintain accurate records of staff absences i.e. sick, FACS & other approved leave - Follow up leave application approvals on a regular basis within 5 days of return to duty. | Ongoing | HT Admin | Accurate records are kept & casual relief is seamlessly directed to appropriate areas |  |  |
|  |  | COMMUNICATION CLIC (SharePoint school intranet) - Implement the use of CLIC as daily communication with staff and students - Upload all school policies and procedures onto CLIC - Promote the regular use of CLIC as the main form of communication - Establish procedures for ensuring accuracy of content - School Website - Establish and maintain systems to ensure currency and accuracy of site - Promote amongst staff, students, parents and community | Term 1 Term 1-4 Term 2 Term 1 Term 1 | C Borg M Leary L Holland G O’Keefe E Nadile C Solis C Borg G Dennaoui |  |  |  |

| MANAGEMENT AREA |  | School and Community Partnership |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| School Priority | Expected Outcomes and Targets | ###### Implementation Strategies | 2010-11 | # Responsibility | Indicators of Success | Allocation $ | Funding source |
| Target 1 | - Community partnerships - School organisation - Bridging the gap between high expectations and student engagement - School Prospectus | Parent/Community/Meetings, Workshops, Communications and Networks TIPS for parenting 4 sessions Term 1-Term 4 - Regular P&C meetings and parent workshops - Invitation letters posted home - Pacific Islander, Parent Network Groups - VET contacts with community | T1-4 T4 | CLOs C Borg J Tsafis | - Number of parents attending workshops and meetings - Evaluations of workshops and training sessions - Student feedback | $36,169 | PSP |
|  | - Community partnerships - School organisation - Bridging the gap between high expectations and student engagement | Promoting the School in the Community The BUZZ Newsletter - Feature column in BUZZ from CLO, performing arts, sport - Training for BUZZ team Media School Promotion - Newspaper articles - Leadership in Media Team - School awards - Work placements: VET | T1, T4 | D Alembakis CLOs D.Clarke T.Pistolis M.Salerno M Voros Community team E Kyritsis | - Newsletter published twice per term - Parent attendance data and evaluations | $4,600 3 days Arabic CLO $21,586.50 | Global PSP |
|  |  | Whole School Activities - Merit Assemblies - Year 6 Orientation - ANZAC Day Service - Girls’ Expo Day - Actively promote parent attendance at School Merit Assemblies, Parent/Teacher Evenings | T1, T2, T4 | D Voros C Borg J Tsafis J.Hardy Year Advisors D.Clarke |  | Release as required | Extra curriculum budget |
|  |  | Celebrations - Planning for 50th Anniversary 2010 - Working parties to collaboratively develop and complete - Roles and responsibilities, time lines, term planner - Planning regular meeting for teams to network and maintain time line. - Invite ex staff and students to participate in the planning and organization of 50th Anniversary - Public Education Day - NAIDOC week activities and celebrations |  | C Clarke CLOs J Tsafis C Borg Management Team CAPA staff All KLA’s SRC J Gibbons | - Increase staff participation - Teacher / student and parent feedback. - Increase communication with whole School. - Student, teacher and parent attendance and participation | Release as required | Extra curriculum budget |
|  |  | Community Events - Bankstown Performing Arts Festival - Revesby Performing Arts festival - Sydney South west Dance festival / camps - Harmony Day - Reclaim the Night ( stop violence against woman) - International Women’s Day, Woman’s festival | T4 | D Clarke M.Salerno CLOs |  | Release as required | Extra curriculum budget |
|  |  | Performance Groups and Events - African, Pacific Islanders, Vietnamese, Indian, Arabic , and Modern Dance groups - School Art Exhibition - Choir - HSC Music/Drama Art Evening - PD/H/PE – DANCE Review | T3, T4 | CLOs D Clarke CAPA staff |  | Release as required | Extra curriculum budget |
| Strengthening community partnerships | To develop partnerships with community organizations that support student social and educational needs and promoting the school in the community | COMMUNITY LIAISON - Attending meetings of community organisations such as: - Arabic welfare Council; Lebanese community Council; Vietnamese community; Centre Link; Pacific Islander Network - Liaise with local community groups and assist with running programs and school relevant to our community e.g. Parenting/First Aids/Road Safety/TAFE - Attending community functions and launch - Biggest Morning Tea - Attending the biggest play group – Homebush - Assist parents with enrolment procedures and attend parent/teacher evening - Translation of school documents and communications into Arabic, Vietnamese and Pacific Island - Phone parents regarding issues of awards, bullying, racism, events, student problems at school, absences, lateness, uniforms etc. - Learning & working to your strengths Project for Pacific Islanders | T 1 – 4 T 1 - 4 | CLO G Dennaoui S Fifita L.Michaelson T.Pistolis CLO’s Year Advisors J.Hardy S Fifita | - Number of parents and students aware of using these services. - Parent attendance data and evaluations - Feedback from parents and staff - Parent support for school programs and policies - Positive resolution of issues - Resolution of parent concerns and questions | 2 days Pacific Islander CLO $7,318.50 | PSP |

| The plan has been endorsed and approved by: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Principal: | Betty Harper | Date: 23 Mar. 09 | School Education Director: | Rod Leonarder | Date: |